## Database
Database Structure
Table name | Usages
admin_permissions | For Admin Permissions
assessments | Create Assesments
assessment_answers | Assesments answer - Subject wise
assessment_questions | Assesments Question - Subject wise
certificates | Certificate detail
chapters | Chapter content - Subject wise
classes | Class list - Board wise
education_boards | Board List
pricing | 6 pricing plan with subscription option
questions_answers | For subject
signup_verify | OPT verification
sold_chapter | Sold chapter and user record
sold_subject | Sold subject and user record
sold_class | Sold class and user record
subjects | Subject Detail
subscriptions | User Subscription records
users | User, SuperAdmin, admin master
user_assessments | Sold Assesments records
user_course_progress | Tracking course progress

## admin
Login page with DB token
JWT Token Authentication
Dashboard | Add /edit/delete - Board
Add /edit/delete - Classes
Add /edit/delete - Subject
| Add /edit/delete - Multiple chapter | Introduction - Text editor
Add Summary - Text editor
Moral - Text editor
Question/Answer - Text editor
Assesment - Free/Paid Option ( 1 Question 4 option - 1 answer )
Video Option - Free/paid - Option to admin
Pdf - Free/paid - Option admin
Add/edit/remove/block - user
Estimate Days | 15

## user
main | Header / menu bar /logo /preloader
Home
Contact
pricing
about
course category
Pricing | course detail page
Chapter wise - 49 INR
Subject wise - 99 INR
Full class wise - 999 INR
User | SignUp/Login with OTP
update Token in DB
Validate token on every task
Dashboard page
Buy chapter/subject/class
assesment attempt portal
show all purchased and in progress course
Certificates
Estimate Days | 20

## api
API
Admin | Login and token auth
Add/edit/remove - Board
Add/edit/remove - Classes
Add/edit/remove - Subject
Add/edit/remove - chapter
Add/edit/remove/block - user
Add/remove - chapter in user account
Add/remove - subject in user account
Add/remove - full class in user account
User | Login and token auth
Show all board
Show all classes - board wise
Show all subject - class wise
Show all chapter - subject wise / lock or free
buy chapter
buy subject
buy full class
fetch user purchase classes
fetch user purchase subject
fetch user purchase chapter
fetch user assesment
fetch user question/answer
fetch user certificate
Estimate Days | 12

## Project cost and timeline
Front-end framework | Next.js
Backend and API's Development | Node.js
Library | React js
Designing | Tailwind CSS
Database | MySQL
Estimate Days | 47
Total Cost | 50 k