## Database
Database Structure
Table name | Usages
admin_permissions | For Admin Permissions
assessments | Create Assesments
assessment_answers | Assesments answer - Subject wise
assessment_questions | Assesments Question - Subject wise
certificates | Certificate detail
chapters | Chapter content - Subject wise
classes | Class list - Board wise
education_boards | Board List
pricing | 6 pricing plan with subscription option
questions_answers | For subject
signup_verify | OPT verification
sold_chapter | Sold chapter and user record
sold_subject | Sold subject and user record
sold_class | Sold class and user record
subjects | Subject Detail
subscriptions | User Subscription records
users | User, SuperAdmin, admin master
user_assessments | Sold Assesments records
user_course_progress | Tracking course progress
Enquiry
Ticket
Blog

## admin
Login page with DB token
JWT Token Authentication
Dashboard | Add /edit/delete - Board
Add /edit/delete - Classes
Add /edit/delete - Subject
| Add /edit/delete - Multiple chapter | Introduction - Text editor
Add Summary - Text editor
Moral - Text editor
Question/Answer - Text editor
Assesment - Free/Paid Option ( 1 Question 4 option - 1 answer )
Video Option - Free/paid - Option to admin
Pdf - Free/paid - Option admin
Add/edit/remove/block - user
Blog
Estimate Days | 15

## user
main | Header / menu bar /logo /preloader
Home
Contact
pricing
about
course category
Blog
Pricing | course detail page
Chapter wise - 49 INR
Subject wise - 199 INR
Full class wise - 999 INR
User | SignUp/Login with OTP
update Token in DB
Validate token on every task
Dashboard page
Buy chapter/subject/class
assesment attempt portal
show all purchased and in progress course
Certificates
Chat
Estimate Days | 20

## api
| API | Status | Total APIs | Date
Admin | Add Create super_amdin and admin and users | Done | 2 | 2025-04-17
| Login and token auth | Done | 4 | 2025-04-17
| Add/edit/remove - Board | Done | 4 | 2025-04-17
| Add/edit/remove - Classes | Done | 4 | 2025-04-17
| Add/edit/remove - Subject | Done | 4 | 2025-04-18
| Add/edit/remove - chapter | Done | 4 | 2025-04-18
| Add/edit/remove/block - user | Done | 1 | 2025-04-18
| Add/update - Chapter in user account | Done | 1 | 2025-04-21
| Add/update - Subject in user account | Done | 1 | 2025-04-21
| Add/update - Full class in user account | Done | 1 | 2025-04-21
| remove - Chapter in user account | Done | 1 | 2025-04-21
| remove - Subject in user account | Done | 1 | 2025-04-21
| remove - Full class in user account | Done | 1 | 2025-04-21
User | Login and token auth | Done | 1 | 2025-04-21
| Show all board | Done | 1 | 2025-04-21
| Show all classes - board wise | Done | 1 | 2025-04-21
| Show all subject - class wise | Done | 1 | 2025-04-21
| Show all chapter - subject wise / lock or free | Done | 1 | 2025-04-21
| buy chapter | Done | 1 | 2025-04-22
| buy subject | Done | 1 | 2025-04-22
| buy full class | Done | 1 | 2025-04-22
| fetch user purchase classes | Done | 1 | 2025-04-22
| fetch user purchase subject | Done | 1 | 2025-04-22
| fetch user purchase chapter - pdf -video url -summary-etc | Done | 1 | 2025-04-22
| fetch user assesment | Done | 1 | 2025-04-22
| fetch user question/answer - without login | Done | 1 | 2025-04-22
fetch user certificate
Estimate Days | 12

## Project cost and timeline
Front-end framework | Next.js
Backend and API's Development | Node.js
Library | React js
Designing | Tailwind CSS
Database | MySQL
Estimate Days | 47
Total Cost | 25K